MISO Expedited Project Review Request Form

Expedited Project Review Request

Please complete the following information:

| Transmission Owner’s / Constructing Entity’s Name | 1803 Electrical Cooperative, Inc |
| --- | --- |
| Project Name | East Mandeville 230/69 kV Substation |
| Project Description | Engineer, Procure, and Construct a new 230/69 kV Substation to serve 1803/WSTE’s Mandeville and Lacombe substations. This new substation removes the need for the Mandeville medium voltage delivery point and provides a new 230kV source to the south side of the 1803/WSTE 69kV system. |
| Load Type (if applicable) | Relocation of an existing Cleco medium voltage delivery point to an 1803/LAGT transmission delivery point |
| Cost | $16,892,500 |
| Reason for Requesting Expedited Review | The existing Mandeville to Lacombe 69kV line is currently operated at 34.5kV and has reached its capacity. The 1803/WSTE long term plans for this area is to convert the Mandeville and Lacombe stations to 69kV operation and extend a 69 kV line from the new East Mandeville 230/69kV Substation through Lacombe to Hickory. 1803 is requesting approval of this project ahead of the MTEP26 cycle so that engineering, procurement, and construction can start in 2026 which is needed to meet the project in service date. |
| Required In-service Date of Project (ISD) | 12/31/2028 |
| Expected lead-time from start of major expenditures to in-service date | 36 months |
| Requested date for inclusion in current cycle MTEP | 10/01/2025 |

Supporting Data Required for Valid Request

Please Specify Status of Supporting Data Submitted to MISO

|  | INCLUDED or DATE Data to be Submitted | File name or MOD Proj Name |
| --- | --- | --- |
| Submission of Transmission Owner planning study | N/A | N/A |
| Submission of project into MISO Project Database (include related MTEP project IDs) | 09/19/2025 | 51070 |
| Submission of model updates to Model on Demand (MOD) | 09/19/2025 | 189460 |
| Submission of available additional information supporting the in-service date requirement | N/A | N/A |
| Dynamic Study – composite load model for any load change | N/A | N/A |
| Contingency Update File | Included | 1803 East Mandeville Substation.con |
| Monitored Element Update File | N/A | N/A |
| One-Line diagram update | N/A | N/A |
| Load Ramp Schedule | Included | Seasonal BLG files |

Please e-mail completed expedited project review request form to one of the MISO Liaison regional representatives shown on the Subregional Planning Meeting (SPM) page of the MISO public website: Subregional Planning Meeting (misoenergy.org)