MISO Expedited Project Review Request Form

Expedited Project Review Request

Please complete the following information:

| Transmission Owner’s / Constructing Entity’s Name | 1803 Electrical Cooperative, Inc |
| --- | --- |
| Project Name | Holton 115/69kV Substation – 115kV Line Breaker and 69kV Bus Tie Breaker Additions |
| Project Description | Add 115kV line breakers, a 69kV bus tie breaker, and associated equipment to the existing 1803 Holton 115/69kV Substation |
| Load Type (if applicable) | N/A |
| Cost | $2,860,000.00 |
| Reason for Requesting Expedited Review | 1803 Electric Cooperative, Inc was approved as a MISO TO on June 12, 2025. This EPR request is for the evaluation of a 2026 MTEP “Baseline Reliability” project to add 115kV line breakers, a 69kV bus tie breaker, and associated equipment to the existing 1803 Holton 115/69kV Substation. Due to expected lead times of BES equipment 1803 requests approval of this project ahead of the MTEP26 cycle. |
| Required In-service Date of Project (ISD) | 06/01/2028 |
| Expected lead-time from start of major expenditures to in-service date | 30 Months |
| Requested date for inclusion in current cycle MTEP | 09/30/2025 |

Supporting Data Required for Valid Request

Please Specify Status of Supporting Data Submitted to MISO

|  | INCLUDED or DATE Data to be Submitted | File name or MOD Proj Name |
| --- | --- | --- |
| Submission of Transmission Owner planning study | N/A | N/A |
| Submission of project into MISO Project Database (include related MTEP project IDs) | 51064 was submitted on 09/19/25 | N/A |
| Submission of model updates to Model on Demand (MOD) | N/A | N/A |
| Submission of available additional information supporting the in-service date requirement | N/A | N/A |
| Dynamic Study – composite load model for any load change | N/A | N/A |
| Contingency Update File | N/A | N/A |
| Monitored Element Update File | N/A | N/A |
| One-Line diagram update | N/A | N/A |
| Load Ramp Schedule | N/A | N/A |

Please e-mail completed expedited project review request form to one of the MISO Liaison regional representatives shown on the Subregional Planning Meeting (SPM) page of the MISO public website: Subregional Planning Meeting (misoenergy.org)